## Advance_Debit Note_Credit Note_
Advance / Debit Note / Credit Note / Retention Release Browse
From 24 Jul 2020 To 23 Oct 2024
Page 1 of 1
Total Records: 34 Records 1 To 34
VType | Voucher No | Date | Contractor | WO_No | Executed_By | Amount | Acc_VNo | AdvVNo | Narration | Remark | status | Approved By | ApproveStatus | RABill_SrNo
Debit Note | 51 | 23 Nov 2023 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -25000 |  |  | Quality debit. |  | Normal | Abhimanyu.shinde | Approved | 107
Debit Note | 61 | 21 Dec 2023 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -100000 |  |  | Absence of Sr. person (Engineer) for Month Sept, Oct, Nov. |  | Normal | Abhimanyu.shinde | Approved | 114
Debit Note | 65 | 16 Dec 2023 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -60000 |  |  | Delayed Completion |  | Normal | shrutika.kumbhar | Approved | 114
Debit Note | 75 | 20 Jan 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -2000 |  |  | Safety debit of 2000/- |  | Normal | shrutika.kumbhar | Approved | 152
Debit Note | 87 | 09 Mar 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -14000 |  |  | Material Wastage |  | Normal | Abhimanyu.shinde | Approved | 237
Debit Note | 112 | 23 May 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -58500 |  |  | 04 debits |  | Normal | Abhimanyu.shinde | Approved | 316
Debit Note | 117 | 02 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -15000 |  |  | TM was expired while casting total loaded qty. 6cum & they are unloaded only 3.5cum. |  | Normal | shrutika.kumbhar | Approved | 341
Debit Note | 118 | 04 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -6264 |  |  | Poor execution & vibrator is not used properly. |  | Normal | shrutika.kumbhar | Approved | 341
Debit Note | 119 | 15 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -2000 |  |  | 8 workers where working without safety shoes at site. |  | Normal | shrutika.kumbhar | Approved | 340
Debit Note | 120 | 24 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -2500 |  |  | bad quality if work & material wastage. |  | Normal | shrutika.kumbhar | Approved | 340
Debit Note | 121 | 17 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -500 |  |  | Work started without induction |  | Normal | shrutika.kumbhar | Approved | 340
Debit Note | 122 | 17 Jun 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -500 |  |  | Working without PPE Kit |  | Normal | shrutika.kumbhar | Approved | 340
Debit Note | 146 | 24 Sep 2024 | Sanskruti Contech Private Limited | 3 | Sanskruti Contech Private Limited | -2500 |  |  | Material got stucked in lift pit.& casting concrete is not dumped |  | Normal | shrutika.kumbhar | Approved | 0
Debit Note | 8 | 12 Sep 2023 | Sanskruti Contech Private Limited | 4 | Sanskruti Contech Private Limited | -5000 |  |  | Safety Debit - Working Without induction on site. By - Sumit Tiwari. CKD (Safety supervisor) |  | Normal | Abhimanyu.shinde | Approved | 61
Debit Note | 153 | 09 Sep 2024 | S K Developers | 21 | S K Developers | -4533 |  |  | Cleaning is not done after work completion |  | Normal | shrutika.kumbhar | Approved | 419
Debit Note | 101 | 13 Feb 2024 | S K Developers | 21 | S K Developers | -3000 |  |  | Debit - 3000/- |  | Normal | shrutika.kumbhar | Approved | 275
Debit Note | 154 | 09 Sep 2024 | Deccan Electricals | 26 | Deccan Electricals | -1355 |  |  | Cleaning not done after work completion |  | Normal | shrutika.kumbhar | Approved | 0
Debit Note | 156 | 01 Jun 2024 | Shreeyash Enterprises | 50 | Shreeyash Enterprises | -2000 |  |  | Safety debit |  | Normal | Abhimanyu.shinde | Approved | 409
Debit Note | 150 | 09 Sep 2024 | Shreeyash Enterprises | 50 | Shreeyash Enterprises | -2855 |  |  | after work completion cleaning not done |  | Normal | shrutika.kumbhar | Approved | 411
Debit Note | 80 | 10 Mar 2023 | Lal Bahadur Sahani | 58 | Lal Bahadur Sahani | -12652.68 |  |  | rate change |  | Normal | shrutika.kumbhar | Approved | 219
Debit Note | 152 | 09 Sep 2024 | Sapna Construction | 63 | Sapna Construction | -2710 |  |  | after work completion cleaning not done |  | Normal | shrutika.kumbhar | Approved | 425
Debit Note | 133 | 10 Aug 2024 | A S Engineering Works | 79 | A S Engineering Works | -21287 | DN - 6 |  | Rate Difference in Item |  | Normal | Abhimanyu.shinde | Approved | 375
Debit Note | 148 | 09 Sep 2024 | S N Decorators | 82 | S N Decorators | -2033 |  |  | after work completion cleaning not done |  | Normal | shrutika.kumbhar | Approved | 0
Debit Note | 109 | 01 Apr 2024 | S N Decorators | 82 | S N Decorators | -2000 | DN - 4 |  | Safety Debit |  | Normal | Abhimanyu.shinde | Approved | 294
Debit Note | 110 | 01 Feb 2024 | S N Decorators | 82 | S N Decorators | -2000 | DN - 4 |  | Safety Debit |  | Normal | Abhimanyu.shinde | Approved | 294
Debit Note | 149 | 09 Sep 2024 | Santosh Kumar Raut | 89 | Santosh Kumar Raut | -1355 |  |  | after work completion cleaning not done |  | Normal | shrutika.kumbhar | Approved | 0
Debit Note | 147 | 09 Sep 2024 | Anjappa Sakhare | 98 | Anjappa Sakhare | -3855 | DN - 12 |  | cleaning is not done after work completion |  | Normal | shrutika.kumbhar | Approved | 422
Debit Note | 159 | 19 Sep 2024 | Anjappa Sakhare | 98 | Anjappa Sakhare | -7285 |  |  | Diff in Qty |  | Normal | Abhimanyu.shinde | Approved | 412
Debit Note | 161 | 07 Oct 2024 | Anjappa Sakhare | 98 | Anjappa Sakhare | -7281 | DN - 12 |  | Qty. Diff. in bill |  | Normal | shrutika.kumbhar | Approved | 422
Debit Note | 131 | 05 Aug 2024 | Anjappa Sakhare | 98 | Anjappa Sakhare | -52847 |  |  | Quantity difference in billed & certified ty. |  | Normal | shrutika.kumbhar | Approved | 362
Debit Note | 151 | 09 Sep 2024 | Ganesh Enterprises | 99 | Ganesh Enterprises | -2855 |  |  | after work completion cleaning not done |  | Normal | shrutika.kumbhar | Approved | 0
Debit Note | 162 | 19 Sep 2024 | SFS Fire Protection India Pvt.Ltd. | 114 | SFS Fire Protection India Pvt.Ltd. | -5000 | DN - 13 |  | Safety Debit |  | Normal | Abhimanyu.shinde | Approved | 437
Debit Note | 163 | 27 May 2024 | SFS Fire Protection India Pvt.Ltd. | 114 | SFS Fire Protection India Pvt.Ltd. | -2000 | DN - 13 |  | Safety Debit |  | Normal | Abhimanyu.shinde | Approved | 437
Debit Note | 164 | 17 Jun 2024 | SFS Fire Protection India Pvt.Ltd. | 114 | SFS Fire Protection India Pvt.Ltd. | -1000 | DN - 13 |  | Safety Debit |  | Normal | Abhimanyu.shinde | Approved | 437