## Advance_Debit Note_Credit Note_
Advance / Debit Note / Credit Note / Retention Release Browse
From 24 Jul 2020 To 23 Oct 2024
Page 1 of 1
Total Records: 21 Records 1 To 21
VType | Voucher No | Date | Contractor | WO_No | Executed_By | Amount | Acc_VNo | AdvVNo | Narration | Remark | status | Approved By | ApproveStatus | RABill_SrNo
Credit Note | 13 | 30 Dec 2023 | Poonam Traders | 23 | Poonam Traders | 236 |  |  | Transportation charges |  | Normal | shrutika.kumbhar | Approved | 37
Debit Note | 52 | 13 Dec 2023 | Jyotirling Infra Projects | 4 | Jyotirling Infra Projects | -31624 | DN - 2 |  | Amount is with GST. Work scope ofJyotirlina but work done by Jadhav Earthmovers. |  | Normal | shrutika.kumbhar | Approved | 101
Debit Note | 62 | 21 Dec 2023 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -100000 |  |  | Absence of Sr. person (Engineer) for Month Sept, Oct, Nov. |  | Normal | Abhimanyu.shinde | Approved | 28
Debit Note | 113 | 27 May 2024 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -10000 |  |  | issue inn quality of work |  | Normal | shrutika.kumbhar | Approved | 131
Debit Note | 132 | 23 May 2024 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -1000 |  |  | Forman & carpenter not using safety equipments |  | Normal | shrutika.kumbhar | Approved | 149
Debit Note | 77 | 04 Oct 2023 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -20000 |  |  | Concrete expired due to delay in casting. Total qty. ordered was M30-6Cum. expired qty.. is 4Cum |  | Normal | shrutika.kumbhar | Approved | 70
Debit Note | 78 | 05 Nov 2023 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -23000 |  |  | SW22, SW23 extra Concreting for this footing , PCC is not done, in as actual size, boom rent, poor supervision. |  | Normal | shrutika.kumbhar | Approved | 69
Debit Note | 85 | 09 Mar 2024 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -5000 | DN - 6 |  | Safety Debit fron CK app | Approved | Normal | Abhimanyu.shinde | Approved | 77
Debit Note | 86 | 09 Mar 2024 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -2000 | DN - 6 |  | Safety Debit by CK app | Approved | Normal | Abhimanyu.shinde | Approved | 77
Debit Note | 99 | 11 Mar 2024 | Sanskruti Contech Private Limited | 10 | Sanskruti Contech Private Limited | -20000 |  |  | Commercial 1st slab was casted on 18th feb but till date 2nd slab is not casted yet. the casting date of 2d slab was 4th march so. we are issuing debit for in 2nd slab casting. |  | Normal | shrutika.kumbhar | Approved | 94
Debit Note | 70 | 15 Jan 2024 | A S Engineering Works | 15 | A S Engineering Works | -5950 |  |  | Quantity Difference Debit Note. |  | Normal | SupportAdmin | Approved | 0
Debit Note | 71 | 15 Jan 2023 | A S Engineering Works | 15 | A S Engineering Works | -7021 |  |  | Quantity Difference Debit |  | Normal | SupportAdmin | Approved | 54
Debit Note | 142 | 30 Aug 2024 | A S Engineering Works | 15 | A S Engineering Works | -7950 |  |  | rate difference |  | Normal | Abhimanyu.shinde | Approved | 156
Debit Note | 73 | 06 Feb 2024 | National Waterproofing Company | 30 | National Waterproofing Company | -3304 | DN - 2 |  | Material Shifting to Contractor by Bobcat |  | Normal | Abhimanyu.shinde | Approved | 58
Debit Note | 74 | 27 Jan 2024 | Diamond Fabricators | 31 | Diamond Fabricators | -1800 |  |  | Rate was finalize for other Qty. but done less Qty. |  | Normal | Abhimanyu.shinde | Approved | 60
Debit Note | 157 | 10 Sep 2024 | Baba Enterprises | 40 | Baba Enterprises | -500 |  |  | Discount |  | Normal | shrutika.kumbhar | Approved | 167
Debit Note | 111 | 22 May 2024 | Kamla Chavan | 46 | Kamla Chavan | -4178 |  |  | Difference in bill rate |  | Normal | shrutika.kumbhar | Approved | 113
Debit Note | 140 | 01 Aug 2024 | Shreeyash Enterprises | 58 | Shreeyash Enterprises | -4050 | DN - 7 |  | Cleaning Not Done |  | Normal | Abhimanyu.shinde | Approved | 152
Debit Note | 143 | 01 Aug 2024 | A S Engineering Works | 59 | A S Engineering Works | -23123 |  |  | Rate difference. |  | Normal | Abhimanyu.shinde | Approved | 157
Other Securities | 2 | 30 Aug 2024 | A S Engineering Works | 15 | A S Engineering Works | 7950 |  |  | Rate difference. |  | Normal | Abhimanyu.shinde | Approved | 0
Other Securities | 1 | 30 Aug 2024 | Shreeyash Enterprises | 58 | Shreeyash Enterprises | 4050 |  |  | After Completion of Work, Cleaning not done. | Approved. | Normal | Abhimanyu.shinde | Approved | 0